## READ ME
CVR-PURSUITS — estimating pipeline framework
WHAT THIS IS
A separate P6 project for the pursuit/estimating pipeline, sharing the CVR-MASTER resource pool.
Pursuits churn weekly — keeping them out of CVR-MASTER protects the execution baseline while the
shared pool shows the bid-vs-billable resource contention in one histogram.
IMPORT ORDER
1. Import CVR_Master_Schedule.xer first (creates the shared resources).
2. Import CVR_Pursuits_Schedule.xer; when prompted on resources, choose 'Keep existing' / match
by resource name so both projects load against the same pool.
3. Schedule both (F9) at data date 12-Aug-26.
LOADING THE ESTIMATING BACKLOG (their Excel)
Paste the estimating spreadsheet into the 'Intake Sheet' tab (one row per estimate), then in P6
copy the matching TEMPLATE WBS (EPC-paired / engineering-only / program) once per row, rename the
activities with the pursuit name, set the SUBMIT milestone's finish-on-or-before constraint to the
bid due date, and assign the estimator. Or send the filled sheet back and the generator rebuilds
the XER with every pursuit included.
ESTIMATE TEMPLATE (CVR-PROC-001 front end)
bid/no-bid gate -> engineering basis (~60% definition) -> takeoffs & material pricing ->
HWC constructability & production-rate review (EPC only) -> pricing & margin review ->
SVP gate -> SUBMIT (constrained to due date).
PLACEHOLDERS TO REPLACE ON TRANSITION
ES1–ES3 estimator resources (name them), Frank Miller confirmed as FM, estimate hour budgets
(currently planning-level), award-decision dates on the four submitted bids.

## Activities
Code | WBS | Activity | Type | Dur (wd) | Start | Finish | Predecessors | Resources (hours) | Constraint
VM-GNG | ACT.VM | VanMeter 161kV + 6mi line — bid/no-bid gate & scope review | Task | 2 | 08/12/26 | 08/13/26 |  | FM 8h; RP 4h
VM-ENG | ACT.VM | VanMeter 161kV + 6mi line — engineering basis for estimate (~60% definition) | Task | 8 | 08/14/26 | 08/25/26 | VM-GNG FS | SSE 60h; KM 24h
VM-TKO | ACT.VM | VanMeter 161kV + 6mi line — quantity takeoffs & material pricing | Task | 6 | 08/19/26 | 08/26/26 | VM-ENG SS+3d | ES1 40h; PLS 12h
VM-CON | ACT.VM | VanMeter 161kV + 6mi line — HWC constructability & production-rate review | Task | 4 | 08/27/26 | 09/01/26 | VM-TKO FS | HPM 16h; ES1 12h
VM-PRC | ACT.VM | VanMeter 161kV + 6mi line — pricing assembly & margin review | Task | 4 | 09/02/26 | 09/07/26 | VM-CON FS; VM-ENG FS | ES1 24h; FM 12h
VM-GTE | ACT.VM | VanMeter 161kV + 6mi line — SVP review gate | Task | 1 | 09/08/26 | 09/08/26 | VM-PRC FS | RP 4h; FM 4h
VM-SUB | ACT.VM | VanMeter 161kV + 6mi line — SUBMIT BID | Finish MS | 0 | 09/09/26 | 09/09/26 | VM-GTE FS |  | finish ≤ 09/04/26
RN-GNG | ACT.RN | Renaissance 345kV MOD switches — bid/no-bid gate & scope review | Task | 2 | 08/12/26 | 08/13/26 |  | FM 8h; RP 4h
RN-ENG | ACT.RN | Renaissance 345kV MOD switches — engineering basis for estimate (~60% definition) | Task | 8 | 08/14/26 | 08/25/26 | RN-GNG FS | SSE 40h; KM 16h
RN-TKO | ACT.RN | Renaissance 345kV MOD switches — quantity takeoffs & material pricing | Task | 6 | 08/19/26 | 08/26/26 | RN-ENG SS+3d | ES2 40h; PLS 12h
RN-CON | ACT.RN | Renaissance 345kV MOD switches — HWC constructability & production-rate review | Task | 4 | 08/27/26 | 09/01/26 | RN-TKO FS | HPM 16h; ES2 12h
RN-PRC | ACT.RN | Renaissance 345kV MOD switches — pricing assembly & margin review | Task | 4 | 09/02/26 | 09/07/26 | RN-CON FS; RN-ENG FS | ES2 24h; FM 12h
RN-GTE | ACT.RN | Renaissance 345kV MOD switches — SVP review gate | Task | 1 | 09/08/26 | 09/08/26 | RN-PRC FS | RP 4h; FM 4h
RN-SUB | ACT.RN | Renaissance 345kV MOD switches — SUBMIT BID | Finish MS | 0 | 09/09/26 | 09/09/26 | RN-GTE FS |  | finish ≤ 09/15/26
FMR-FLW | SUB | Steuben Frontier Make Ready ($100K CVR) — award follow-up & clarifications | Task | 3 | 09/16/26 | 09/18/26 |  | FM 8h; RP 4h | start ≥ 09/16/26
FMR-AWD | SUB | Steuben Frontier Make Ready ($100K CVR) — award decision (expected) | Milestone | 0 | 09/30/26 | 09/30/26 | FMR-FLW FS |  | start ≥ 09/30/26
JG-FLW | SUB | Hoosier Jacksonburg–Gateway ($160K CVR / $3.55M EPC) — award follow-up & clarifications | Task | 3 | 11/02/26 | 11/04/26 |  | FM 8h; RP 4h | start ≥ 11/02/26
JG-AWD | SUB | Hoosier Jacksonburg–Gateway ($160K CVR / $3.55M EPC) — award decision (expected) | Milestone | 0 | 11/16/26 | 11/16/26 | JG-FLW FS |  | start ≥ 11/16/26
RR-FLW | SUB | Hoosier Rosehill–Rockport ($290K CVR / $5.59M EPC) — award follow-up & clarifications | Task | 3 | 11/02/26 | 11/04/26 |  | FM 8h; RP 4h | start ≥ 11/02/26
RR-AWD | SUB | Hoosier Rosehill–Rockport ($290K CVR / $5.59M EPC) — award decision (expected) | Milestone | 0 | 11/16/26 | 11/16/26 | RR-FLW FS |  | start ≥ 11/16/26
LBW-FLW | SUB | Lansing BWL Joint Use Audit ($1,350K CVR) — award follow-up & clarifications | Task | 3 | 11/16/26 | 11/18/26 |  | FM 8h; RP 4h | start ≥ 11/16/26
LBW-AWD | SUB | Lansing BWL Joint Use Audit ($1,350K CVR) — award decision (expected) | Milestone | 0 | 11/30/26 | 11/30/26 | LBW-FLW FS |  | start ≥ 11/30/26
TE-GNG | TMP.EPC | [TEMPLATE] EPC-paired estimate — bid/no-bid gate & scope review | Task | 2 | 12/01/27 | 12/02/27 |  | FM 8h; RP 4h | start ≥ 12/01/27
TE-ENG | TMP.EPC | [TEMPLATE] EPC-paired estimate — engineering basis for estimate (~60% definition) | Task | 8 | 12/03/27 | 12/14/27 | TE-GNG FS | SSE 60h; KM 24h
TE-TKO | TMP.EPC | [TEMPLATE] EPC-paired estimate — quantity takeoffs & material pricing | Task | 6 | 12/08/27 | 12/15/27 | TE-ENG SS+3d | ES1 40h; PLS 12h
TE-CON | TMP.EPC | [TEMPLATE] EPC-paired estimate — HWC constructability & production-rate review | Task | 4 | 12/16/27 | 12/21/27 | TE-TKO FS | HPM 16h; ES1 12h
TE-PRC | TMP.EPC | [TEMPLATE] EPC-paired estimate — pricing assembly & margin review | Task | 4 | 12/22/27 | 12/27/27 | TE-CON FS; TE-ENG FS | ES1 24h; FM 12h
TE-GTE | TMP.EPC | [TEMPLATE] EPC-paired estimate — SVP review gate | Task | 1 | 12/28/27 | 12/28/27 | TE-PRC FS | RP 4h; FM 4h
TE-SUB | TMP.EPC | [TEMPLATE] EPC-paired estimate — SUBMIT BID | Finish MS | 0 | 12/29/27 | 12/29/27 | TE-GTE FS
TN-GNG | TMP.ENG | [TEMPLATE] engineering-only estimate — bid/no-bid gate & scope review | Task | 2 | 12/01/27 | 12/02/27 |  | FM 8h; RP 4h | start ≥ 12/01/27
TN-ENG | TMP.ENG | [TEMPLATE] engineering-only estimate — engineering basis for estimate (~60% definition) | Task | 8 | 12/03/27 | 12/14/27 | TN-GNG FS | TLE 40h; KM 16h
TN-TKO | TMP.ENG | [TEMPLATE] engineering-only estimate — quantity takeoffs & material pricing | Task | 6 | 12/08/27 | 12/15/27 | TN-ENG SS+3d | ES2 40h; PLS 12h
TN-PRC | TMP.ENG | [TEMPLATE] engineering-only estimate — pricing assembly & margin review | Task | 4 | 12/16/27 | 12/21/27 | TN-TKO FS; TN-ENG FS | ES2 24h; FM 12h
TN-GTE | TMP.ENG | [TEMPLATE] engineering-only estimate — SVP review gate | Task | 1 | 12/22/27 | 12/22/27 | TN-PRC FS | RP 4h; FM 4h
TN-SUB | TMP.ENG | [TEMPLATE] engineering-only estimate — SUBMIT BID | Finish MS | 0 | 12/23/27 | 12/23/27 | TN-GTE FS
TP-GNG | TMP.PRG | [TEMPLATE] program pursuit — qualification & scope | Task | 5 | 12/01/27 | 12/07/27 |  | FM 12h; RP 8h | start ≥ 12/01/27
TP-EST | TMP.PRG | [TEMPLATE] program pursuit — basis of estimate & unit rates | Task | 10 | 12/08/27 | 12/21/27 | TP-GNG FS | ES3 60h; TLE 24h
TP-PRC | TMP.PRG | [TEMPLATE] program pursuit — pricing & terms | Task | 5 | 12/22/27 | 12/28/27 | TP-EST FS | ES3 24h; FM 12h
TP-SUB | TMP.PRG | [TEMPLATE] program pursuit — SUBMIT | Finish MS | 0 | 12/29/27 | 12/29/27 | TP-PRC FS
OP-TRN | OPS | Estimating transition into CVR (on Decision 2) — people, tools, files | Task | 45 | 09/01/26 | 11/02/26 |  | FM 80h; RP 40h; SPM 24h | start ≥ 09/01/26
OP-LOG | OPS | Load estimating backlog from Excel into this project (intake sheet) | Task | 10 | 09/08/26 | 09/21/26 | OP-TRN SS+5d | FM 24h; SPM 16h
OP-WKL | OPS | Weekly pursuit review cadence (P6-driven, through 2027) | Task | 350 | 08/17/26 | 12/17/27 |  | FM 150h; RP 70h; SPM 70h | start ≥ 08/17/26

## Intake Sheet
Pursuit / estimate name | Customer | Type (EPC / ENG / PROG) | Bid due date | Est. contract value ($K) | CVR scope ($K) | Estimator | Engineering support (name) | Eng hours | Est hours | Status (active / hold / submitted) | Notes
⟵ paste the estimating backlog here, one row per estimate
Types map to the P6 templates: EPC = EPC-paired (with HWC constructability review) · ENG = engineering-only · PROG = program/audit. Send this sheet back filled and the generator rebuilds the XER with every row as a scheduled pursuit.

## Resource Pool
ID | Short | Resource | Shared with CVR-MASTER?
1 | RP | Roy Pierce — Principal Engineer | shared
2 | HW | Hayley Worthen — Senior Engineer | shared
4 | BP | Bhkti Patel — Engineer III | shared
5 | FW | Francis Wagner — Engineer III | shared
7 | CP | Craig Peterson — Engineer I | shared
8 | KM | Kevin Metts — Designer II | shared
11 | SPM | Senior PM (starts 8/24) | shared
12 | TLE | T-Line Engineer (open req) | shared
13 | SSE | Substation Engineer (open req) | shared
14 | STE | Structural Engineer (open req) | shared
16 | PLS | PLS Procurement | shared
17 | HPM | HWC Construction PM (coordination) | shared
18 | FM | Frank Miller — Director of Estimating | NEW — estimating
19 | ES1 | Estimator 1 (placeholder — name on transition) | NEW — estimating
20 | ES2 | Estimator 2 (placeholder — name on transition) | NEW — estimating
21 | ES3 | Estimator 3 (placeholder — name on transition) | NEW — estimating
Import CVR-MASTER first; match resources by name on this import so both projects load one pool and the combined histogram shows bid-vs-billable contention.