## READ ME
CVR Master Schedule — P6 import package
FILES
CVR_Master_Schedule.xer — import into P6: File > Import > Primavera XER, project CVR-MASTER.
This workbook — the human-readable register of everything in the XER.
WHAT'S IN THE SCHEDULE
106 activities across CenterPoint direct (017 jobs), DTE (New Baltimore 39-WO pilot, Catalina,
Renaissance), Consumers (HVD sensors, Pole Replacement EPC), MEC EPC support (Sub P, Enterprise Way,
VanMeter), Cloverland closeout, the pending pipeline (constrained to assumed award dates), and governance.
Every procurement chain follows CVR-PROC-001: IFC -> EOR transmittal -> PLS PO -> lead time -> delivery,
so the 'engineering complete' milestones are wired to construction need dates through real lead times.
RESOURCE LOADING
Loaded with the current 13-person roster plus: Senior PM (starts 8/24), and the three open reqs
(T-Line, Substation, Structural) as placeholder resources — their assignments show the hiring need.
Hours are planning-level estimates; refine per job as the PM team baselines.
AFTER IMPORT (P6)
1. Schedule (F9) at data date 12-Aug-26 — P6 recomputes the network from the logic.
2. Review constraint dates (assumed award dates on Renaissance/VanMeter/pipeline; construction need dates).
3. Set the baseline, then run weekly updates per the operating cadence.
ASSUMED DATES TO CONFIRM
VanMeter award 10/15/26 · Renaissance award 11/2/26 · NB construction 4/1/27 · Pole program construction
3/1/27 · pipeline awards Q4-26. Adjust the milestones and re-schedule.

## Activities
Code | WBS | Activity | Type | Dur (wd) | Start | Finish | Predecessors | Resources (hours) | Constraint
GW-CLO | CPE.GW | Gateway 69kV — final billing & record prints | Task | 15 | 08/12/26 | 09/01/26 |  | BP 40h; CA 24h
GW-FIN | CPE.GW | Gateway 69kV complete | Finish MS | 0 | 09/02/26 | 09/02/26 | GW-CLO FS
RK-CLO | CPE.RK | Rockport 69kV — closeout & record prints | Task | 15 | 08/12/26 | 09/01/26 |  | BP 24h; CA 16h
RK-FIN | CPE.RK | Rockport 69kV complete | Finish MS | 0 | 09/02/26 | 09/02/26 | RK-CLO FS
AM-CLO | CPE.AM | Angel Mounds — record prints & closeout | Task | 20 | 08/12/26 | 09/08/26 |  | TN 24h; CA 16h
AM-FIN | CPE.AM | Angel Mounds complete | Finish MS | 0 | 09/09/26 | 09/09/26 | AM-CLO FS
NW-60 | CPE.NW | Northwest — 60% design (cap banks + protection) | Task | 45 | 08/12/26 | 10/13/26 |  | BP 220h; KM 160h; CA 60h
NW-90 | CPE.NW | Northwest — 90% design & CenterPoint review | Task | 40 | 10/14/26 | 12/08/26 | NW-60 FS | BP 160h; KM 120h
NW-IFC | CPE.NW | Northwest — IFC issued (engineering complete) | Milestone | 0 | 12/22/26 | 12/22/26 | NW-90 FS+10d
NW-CB-TRN | CPE.NW | EOR transmittal to PLS — 69kV capacitor banks | Task | 5 | 12/23/26 | 12/29/26 | NW-IFC FS | BP 16h; PLS 8h
NW-CB-PO | CPE.NW | PO placed — 69kV capacitor banks | Task | 15 | 12/30/26 | 01/19/27 | NW-CB-TRN FS | PLS 24h
NW-CB-FAB | CPE.NW | Fabrication & lead time — 69kV capacitor banks (30 wks) | Task | 150 | 01/20/27 | 08/17/27 | NW-CB-PO FS | PLS 8h
NW-CB-DLV | CPE.NW | Delivery on site — 69kV capacitor banks | Milestone | 0 | 08/18/27 | 08/18/27 | NW-CB-FAB FS |  | 05/03/27
NW-SUP | CPE.NW | Northwest — construction support & energization | Task | 60 | 08/19/27 | 11/10/27 | NW-CB-DLV FS | BP 80h; SPM 60h
NW-FIN | CPE.NW | Northwest 69kV complete | Finish MS | 0 | 11/11/27 | 11/11/27 | NW-SUP FS
LR-60 | CPE.LR | Leonard Rd — 60% design (2 cap banks + breaker-and-a-half) | Task | 50 | 08/12/26 | 10/20/26 |  | FW 240h; KM 160h; CA 60h
LR-90 | CPE.LR | Leonard Rd — 90% design & CenterPoint review | Task | 40 | 10/21/26 | 12/15/26 | LR-60 FS | FW 160h; KM 120h
LR-IFC | CPE.LR | Leonard Rd — IFC issued (engineering complete) | Milestone | 0 | 12/29/26 | 12/29/26 | LR-90 FS+10d
LR-CB-TRN | CPE.LR | EOR transmittal to PLS — 69kV capacitor banks | Task | 5 | 12/30/26 | 01/05/27 | LR-IFC FS | FW 16h; PLS 8h
LR-CB-PO | CPE.LR | PO placed — 69kV capacitor banks | Task | 15 | 01/06/27 | 01/26/27 | LR-CB-TRN FS | PLS 24h
LR-CB-FAB | CPE.LR | Fabrication & lead time — 69kV capacitor banks (30 wks) | Task | 150 | 01/27/27 | 08/24/27 | LR-CB-PO FS | PLS 8h
LR-CB-DLV | CPE.LR | Delivery on site — 69kV capacitor banks | Milestone | 0 | 08/25/27 | 08/25/27 | LR-CB-FAB FS |  | 07/06/27
LR-SUP | CPE.LR | Leonard Rd — construction support & energization | Task | 60 | 08/26/27 | 11/17/27 | LR-CB-DLV FS | FW 80h; SPM 60h
LR-FIN | CPE.LR | Leonard Rd 69kV complete | Finish MS | 0 | 11/18/27 | 11/18/27 | LR-SUP FS
NB-PIL | DTE.NB | CVR-PROC-001 pilot kickoff (one schedule, one cost picture) | Task | 10 | 08/12/26 | 08/25/26 |  | SPM 40h; RP 16h; HPM 16h
NB-WO1 | DTE.NB | WO packages — batch 1 (12 WOs) engineering complete | Task | 55 | 08/19/26 | 11/03/26 | NB-PIL SS+5d | HW 300h; KM 200h; CA 120h
NB-WO2 | DTE.NB | WO packages — batch 2 (14 WOs) engineering complete | Task | 55 | 11/04/26 | 01/19/27 | NB-WO1 FS | HW 300h; KM 200h; CA 120h
NB-WO3 | DTE.NB | WO packages — batch 3 (13 WOs) engineering complete | Task | 50 | 01/20/27 | 03/30/27 | NB-WO2 FS | HW 260h; KM 180h; CA 100h
NB-IFC | DTE.NB | New Baltimore — all 39 WOs IFC (engineering complete) | Milestone | 0 | 03/31/27 | 03/31/27 | NB-WO3 FS
NB-PL-TRN | DTE.NB | EOR transmittal to PLS — distribution/transmission poles | Task | 5 | 11/04/26 | 11/10/26 | NB-WO1 FS | HW 16h; PLS 8h
NB-PL-PO | DTE.NB | PO placed — distribution/transmission poles | Task | 15 | 11/11/26 | 12/01/26 | NB-PL-TRN FS | PLS 24h
NB-PL-FAB | DTE.NB | Fabrication & lead time — distribution/transmission poles (16 wks) | Task | 80 | 12/02/26 | 03/23/27 | NB-PL-PO FS | PLS 8h
NB-PL-DLV | DTE.NB | Delivery on site — distribution/transmission poles | Milestone | 0 | 03/24/27 | 03/24/27 | NB-PL-FAB FS |  | 03/15/27
NB-CD-TRN | DTE.NB | EOR transmittal to PLS — conductor / OPGW / hardware | Task | 5 | 11/04/26 | 11/10/26 | NB-WO1 FS | HW 16h; PLS 8h
NB-CD-PO | DTE.NB | PO placed — conductor / OPGW / hardware | Task | 15 | 11/11/26 | 12/01/26 | NB-CD-TRN FS | PLS 24h
NB-CD-FAB | DTE.NB | Fabrication & lead time — conductor / OPGW / hardware (16 wks) | Task | 80 | 12/02/26 | 03/23/27 | NB-CD-PO FS | PLS 8h
NB-CD-DLV | DTE.NB | Delivery on site — conductor / OPGW / hardware | Milestone | 0 | 03/24/27 | 03/24/27 | NB-CD-FAB FS |  | 03/15/27
NB-SRP | DTE.NB | Material surplus triage & BOM-vs-actual reconciliation | Task | 30 | 08/12/26 | 09/22/26 | NB-PIL SS | HW 60h; PLS 60h; EST 40h
NB-OBK | DTE.NB | DTE open-book response & cost-per-mile benchmark | Task | 25 | 08/26/26 | 09/29/26 | NB-SRP SS+10d | SPM 60h; EST 60h; RP 20h
NB-CON | DTE.NB | Spring 2027 construction start (HWC) | Milestone | 0 | 04/01/27 | 04/01/27 | NB-PL-DLV FS; NB-CD-DLV FS |  | 04/01/27
NB-SUP | DTE.NB | Construction support — 2027 season | Task | 175 | 04/02/27 | 12/02/27 | NB-CON FS | HW 300h; SPM 350h; KM 120h
NB-FIN | DTE.NB | New Baltimore complete | Finish MS | 0 | 12/03/27 | 12/03/27 | NB-SUP FS
CT-SUP | DTE.CT | Catalina Ph 3 — construction support tail | Task | 95 | 08/12/26 | 12/22/26 |  | HW 120h
CT-FIN | DTE.CT | Catalina Ph 3 complete | Finish MS | 0 | 12/23/26 | 12/23/26 | CT-SUP FS
RN-BID | DTE.RN | Renaissance 345kV — bid preparation & submittal | Task | 24 | 08/12/26 | 09/14/26 |  | RP 60h; EST 80h; SSE 40h
RN-AWD | DTE.RN | Award (assumed) | Milestone | 0 | 11/02/26 | 11/02/26 | RN-BID FS |  | 11/02/26
RN-DSN | DTE.RN | MOD switch replacement design — 60/90/IFC | Task | 65 | 11/03/26 | 02/01/27 | RN-AWD FS | SSE 320h; KM 160h; RP 40h
RN-IFC | DTE.RN | Renaissance — IFC issued (engineering complete) | Milestone | 0 | 02/02/27 | 02/02/27 | RN-DSN FS
RN-MS-TRN | DTE.RN | EOR transmittal to PLS — 345kV MOD switches (6) | Task | 5 | 02/03/27 | 02/09/27 | RN-IFC FS | SSE 16h; PLS 8h
RN-MS-PO | DTE.RN | PO placed — 345kV MOD switches (6) | Task | 15 | 02/10/27 | 03/02/27 | RN-MS-TRN FS | PLS 24h
RN-MS-FAB | DTE.RN | Fabrication & lead time — 345kV MOD switches (6) (40 wks) | Task | 200 | 03/03/27 | 12/07/27 | RN-MS-PO FS | PLS 8h
RN-MS-DLV | DTE.RN | Delivery on site — 345kV MOD switches (6) | Milestone | 0 | 12/08/27 | 12/08/27 | RN-MS-FAB FS |  | 09/01/27
RN-OUT | DTE.RN | Fall 2027 outage — switch replacement support | Task | 45 | 12/09/27 | 02/09/28 | RN-MS-DLV FS | SSE 120h; SPM 80h | 10/01/27
RN-FIN | DTE.RN | Renaissance complete | Finish MS | 0 | 02/10/28 | 02/10/28 | RN-OUT FS
HV-DEV | CON.HVD | HVD sensors — record prints & BOM closeout | Task | 55 | 08/12/26 | 10/27/26 |  | CP 160h; CA 60h
HV-FIN | CON.HVD | HVD Line Sensors complete | Finish MS | 0 | 10/28/26 | 10/28/26 | HV-DEV FS
PR-KO | CON.PR | Pole program kickoff with HWC (EPC-paired) | Task | 5 | 09/08/26 | 09/14/26 |  | SPM 24h; RP 8h; HPM 16h | 09/08/26
PR-DSN | CON.PR | Design packages — 168 poles (staking, framing, guying) | Task | 70 | 09/15/26 | 12/21/26 | PR-KO FS | TLE 400h; CP 300h; KM 200h; CA 100h
PR-IFC | CON.PR | Pole program — IFC issued (engineering complete) | Milestone | 0 | 12/22/26 | 12/22/26 | PR-DSN FS
PR-PL-TRN | CON.PR | EOR transmittal to PLS — distribution/transmission poles | Task | 5 | 12/23/26 | 12/29/26 | PR-IFC FS | TLE 16h; PLS 8h
PR-PL-PO | CON.PR | PO placed — distribution/transmission poles | Task | 15 | 12/30/26 | 01/19/27 | PR-PL-TRN FS | PLS 24h
PR-PL-FAB | CON.PR | Fabrication & lead time — distribution/transmission poles (16 wks) | Task | 80 | 01/20/27 | 05/11/27 | PR-PL-PO FS | PLS 8h
PR-PL-DLV | CON.PR | Delivery on site — distribution/transmission poles | Milestone | 0 | 05/12/27 | 05/12/27 | PR-PL-FAB FS |  | 03/01/27
PR-CON | CON.PR | HWC construction — 2027 season | Milestone | 0 | 05/13/27 | 05/13/27 | PR-PL-DLV FS |  | 03/01/27
PR-SUP | CON.PR | Construction support & closeout documentation | Task | 180 | 05/14/27 | 01/20/28 | PR-CON FS | TLE 200h; CP 160h; SPM 200h
PR-FIN | CON.PR | Pole Replacement program complete | Finish MS | 0 | 01/21/28 | 01/21/28 | PR-SUP FS
SP-IFC2 | MEC.SP | Sub P — Phase 2 IFC comments & final issue | Task | 20 | 08/12/26 | 09/08/26 |  | SSE 80h; KM 40h
SP-SUP | MEC.SP | Sub P — construction & energization support | Task | 55 | 08/12/26 | 10/27/26 | SP-IFC2 SS | SSE 100h; RD 40h
SP-FIN | MEC.SP | Sub P GSU complete | Finish MS | 0 | 10/28/26 | 10/28/26 | SP-SUP FS
EW-ASB | MEC.EW | Enterprise Way — as-builts & punch list | Task | 30 | 08/12/26 | 09/22/26 |  | RD 60h; CA 30h
EW-FIN | MEC.EW | Enterprise Way complete | Finish MS | 0 | 09/23/26 | 09/23/26 | EW-ASB FS
VM-BID | MEC.VM | VanMeter — bid preparation & submittal (with HWC) | Task | 17 | 08/12/26 | 09/03/26 |  | RP 60h; EST 100h; SSE 60h; TLE 40h
VM-AWD | MEC.VM | Award (assumed) | Milestone | 0 | 10/15/26 | 10/15/26 | VM-BID FS |  | 10/15/26
VM-30 | MEC.VM | VanMeter — 30% design (substation + 6mi 161kV line) | Task | 45 | 10/16/26 | 12/17/26 | VM-AWD FS | SSE 240h; TLE 240h; KM 120h; STE 80h
VM-60 | MEC.VM | VanMeter — 60% design | Task | 45 | 12/18/26 | 02/18/27 | VM-30 FS | SSE 240h; TLE 240h; KM 160h; STE 120h
VM-90 | MEC.VM | VanMeter — 90% design & MEC review | Task | 40 | 02/19/27 | 04/15/27 | VM-60 FS | SSE 200h; TLE 200h; KM 120h
VM-IFC | MEC.VM | VanMeter — IFC issued (engineering complete) | Milestone | 0 | 04/29/27 | 04/29/27 | VM-90 FS+10d
VM-XF-TRN | MEC.VM | EOR transmittal — 161kV transformer (early release at 60%) | Task | 5 | 02/19/27 | 02/25/27 | VM-60 FS | SSE 16h; PLS 8h
VM-XF-PO | MEC.VM | PO placed — 161kV transformer | Task | 15 | 02/26/27 | 03/18/27 | VM-XF-TRN FS | PLS 24h
VM-XF-FAB | MEC.VM | Fabrication & lead — 161kV transformer (60 wks) | Task | 300 | 03/19/27 | 05/11/28 | VM-XF-PO FS | PLS 8h
VM-XF-DLV | MEC.VM | Delivery on site — 161kV transformer | Milestone | 0 | 05/12/28 | 05/12/28 | VM-XF-FAB FS |  | 03/01/28
VM-BK-TRN | MEC.VM | EOR transmittal — HV breakers (early release at 60%) | Task | 5 | 02/19/27 | 02/25/27 | VM-60 FS | SSE 12h; PLS 8h
VM-BK-PO | MEC.VM | PO placed — HV breakers | Task | 15 | 02/26/27 | 03/18/27 | VM-BK-TRN FS | PLS 16h
VM-BK-FAB | MEC.VM | Fabrication & lead — HV breakers (38 wks) | Task | 190 | 03/19/27 | 12/09/27 | VM-BK-PO FS | PLS 8h
VM-BK-DLV | MEC.VM | Delivery on site — HV breakers | Milestone | 0 | 12/10/27 | 12/10/27 | VM-BK-FAB FS
VM-ST-TRN | MEC.VM | EOR transmittal to PLS — substation steel structures | Task | 5 | 04/30/27 | 05/06/27 | VM-IFC FS | SSE 16h; PLS 8h
VM-ST-PO | MEC.VM | PO placed — substation steel structures | Task | 15 | 05/07/27 | 05/27/27 | VM-ST-TRN FS | PLS 24h
VM-ST-FAB | MEC.VM | Fabrication & lead time — substation steel structures (24 wks) | Task | 120 | 05/28/27 | 11/11/27 | VM-ST-PO FS | PLS 8h
VM-ST-DLV | MEC.VM | Delivery on site — substation steel structures | Milestone | 0 | 11/12/27 | 11/12/27 | VM-ST-FAB FS |  | 10/01/27
VM-RL-TRN | MEC.VM | EOR transmittal to PLS — relay & control panels | Task | 5 | 04/30/27 | 05/06/27 | VM-IFC FS | SSE 16h; PLS 8h
VM-RL-PO | MEC.VM | PO placed — relay & control panels | Task | 15 | 05/07/27 | 05/27/27 | VM-RL-TRN FS | PLS 24h
VM-RL-FAB | MEC.VM | Fabrication & lead time — relay & control panels (26 wks) | Task | 130 | 05/28/27 | 11/25/27 | VM-RL-PO FS | PLS 8h
VM-RL-DLV | MEC.VM | Delivery on site — relay & control panels | Milestone | 0 | 12/01/27 | 12/01/27 | VM-RL-FAB FS |  | 12/01/27
VM-CON | MEC.VM | HWC construction start (site/civil) | Milestone | 0 | 06/01/27 | 06/01/27 | VM-IFC FS |  | 06/01/27
VM-SUP | MEC.VM | Construction support through energization | Task | 250 | 06/02/27 | 05/16/28 | VM-CON FS | SSE 300h; TLE 200h; SPM 300h
VM-FIN | MEC.VM | VanMeter complete | Finish MS | 0 | 05/17/28 | 05/17/28 | VM-SUP FS; VM-XF-DLV FS
CL-CLO | CLV | Manistique — record prints & final closeout | Task | 30 | 08/12/26 | 09/22/26 |  | TN 60h; CA 24h
CL-FIN | CLV | Manistique complete | Finish MS | 0 | 09/23/26 | 09/23/26 | CL-CLO FS
PP-LBW | PIPE | Lansing BWL Joint Use Audit — execution (on award, assumed Q4-26) | Task | 260 | 11/16/26 | 11/12/27 |  | TLE 800h; CP 600h; AH 400h | 11/16/26
PP-JG | PIPE | Hoosier Jacksonburg–Gateway — engineering (on award) | Task | 120 | 12/01/26 | 05/17/27 |  | TLE 300h; KM 160h | 12/01/26
PP-RR | PIPE | Hoosier Rosehill–Rockport — engineering (on award) | Task | 140 | 01/04/27 | 07/16/27 |  | TLE 360h; KM 200h | 01/04/27
PP-FMR | PIPE | Steuben Frontier Make Ready — 10 packages (on award) | Task | 90 | 10/01/26 | 02/03/27 |  | CP 300h; AH 200h | 10/01/26
GV-QAQ | GOV | Stand up design QA/QC review gates | Task | 15 | 08/17/26 | 09/04/26 |  | RP 40h; HW 24h | 08/17/26
GV-EST | GOV | Estimating transition into CVR (on Decision 2) | Task | 45 | 09/01/26 | 11/02/26 |  | RP 60h; EST 120h; SPM 40h | 09/01/26
GV-P6 | GOV | P6 master schedule live — baseline set, weekly update cadence | Task | 10 | 08/24/26 | 09/04/26 |  | SPM 60h | 08/24/26
GV-MO | GOV | Monthly close / KPI / forecast cadence (through 2027) | Task | 355 | 08/17/26 | 12/24/27 |  | SPM 200h; RP 100h | 08/17/26

## Long-Lead Register
Equipment | Job / element | Lead (wks) | Construction need | PO must be placed by | Transmittal by | ENGINEERING COMPLETE BY | IFC forecast (schedule) | Margin (wd)
69kV capacitor banks | CenterPoint Northwest 69kV | 30 | 05/03/27 | 10/05/26 | 09/14/26 | 09/07/26 | 12/22/26 | -76
69kV capacitor banks | CenterPoint Leonard Rd 69kV | 30 | 07/06/27 | 12/08/26 | 11/17/26 | 11/10/26 | 12/29/26 | -35
distribution/transmission poles | DTE New Baltimore (rolling, batch 1) | 16 | 03/15/27 | 11/23/26 | 11/02/26 | 10/26/26 | 11/03/26 | -6
conductor / OPGW / hardware | DTE New Baltimore (rolling, batch 1) | 16 | 03/15/27 | 11/23/26 | 11/02/26 | 10/26/26 | 11/03/26 | -6
345kV MOD switches (6) | DTE Renaissance 345kV | 40 | 09/01/27 | 11/25/26 | 11/04/26 | 10/28/26 | 02/02/27 | -69
distribution/transmission poles | Consumers Pole Replacements | 16 | 03/01/27 | 11/09/26 | 10/19/26 | 10/12/26 | 12/22/26 | -51
161kV power transformer | MEC VanMeter (early release @60%) | 60 | 03/01/28 | 01/06/27 | 12/16/26 | 12/09/26 | 02/18/27 | -51
HV breakers (69–161kV) | MEC VanMeter (early release @60%) | 38 | 11/01/27 | 02/08/27 | 01/18/27 | 01/11/27 | 02/18/27 | -28
substation steel structures | MEC VanMeter | 24 | 10/01/27 | 04/16/27 | 03/26/27 | 03/19/27 | 04/29/27 | -29
relay & control panels | MEC VanMeter | 26 | 12/01/27 | 06/02/27 | 05/12/27 | 05/05/27 | 04/29/27 | 4
ENGINEERING COMPLETE BY = construction need − fabrication lead − PO cycle (3 wks) − transmittal (1 wk). Negative margin = the schedule's forecast IFC is later than procurement requires — pull design left or expedite.

## Resource Loading
Resource | Role / note | Total hours | ≈ FTE-months (146 h/mo @ 84%)
RP | Roy Pierce — Principal Engineer | 404 | 2.8
HW | Hayley Worthen — Senior Engineer | 1396 | 9.6
RD | Randy Pynenberg — Engineer IV | 100 | 0.7
BP | Bhkti Patel — Engineer III | 540 | 3.7
FW | Francis Wagner — Engineer III | 496 | 3.4
TN | Taylor Nelson — Engineer II | 84 | 0.6
CP | Craig Peterson — Engineer I | 1520 | 10.4
KM | Kevin Metts — Designer II | 2420 | 16.6
CA | Collin Allen — Graphics Technician | 730 | 5
AH | Auston Hopson — Graphics Technician | 600 | 4.1
SPM | Senior PM (starts 8/24) | 1474 | 10.1
TLE | T-Line Engineer (open req) | 2996 | 20.5
SSE | Substation Engineer (open req) | 1776 | 12.2
STE | Structural Engineer (open req) | 200 | 1.4
EST | CVR Estimating (per CVR-PROC-001) | 400 | 2.7
PLS | PLS Procurement | 452 | 3.1
HPM | HWC Construction PM (coordination) | 32 | 0.2
Assignments spread evenly across each activity in P6; open-req rows (TLE/SSE/STE) quantify the hiring need — reassign to named staff as they start.